## Gantt Chart Template
| PROJECT TITLE | Parking Infrastructure |  |  |  | COMPANY NAME | [8 empty] | UCSC
| PROJECT MANAGER | Scott Birss |  |  |  | DATE | [8 empty] | 2018-01-24
[6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter | Team | 2018-01-18 | 2018-01-26 | 100% | bar: WEEK 2 R to WEEK 3 F
1.2 | Block Diagram | Team | 2018-01-26 | 2018-01-26 | 100% | bar: WEEK 2 R to WEEK 3 F
1.3 | Block Diagram revisions & Part List | Team | 2018-01-26 | 2018-02-02 | 0% | bar: WEEK 4 R to WEEK 5 T
1.4 | Budget & Discuss API interface Development | Team | 2018-01-29 | 2018-02-02 | 0% | bar: WEEK 4 M to WEEK 4 F
1.5 | Implement API | Team | 2018-02-02 | 2018-02-09 | 0%
1.6 | create specifcations sheets for all subsystems | Team | 2018-02-09 | 2018-02-16
1.7 | finish implemenation of prototype model | Team | 2018-02-16 | 2018-02-23
1.8 | develop testing phase & modify as needed | Team | 2018-02-23 | 2018-03-02
1.9 | finalize prototyped product with casing | Team | 2018-03-02 | 2018-03-09
2 | Hardware
2.1.1 | Basic Sensors working on PSoC | Scott | 2018-02-02 | 2018-02-09 | 100% | bar: WEEK 4 M to WEEK 5 F
2.1.2 | Develop API for Camera | David | 2018-02-02 | 2018-02-09 | bar: WEEK 4 M to WEEK 4 F
2.2.1 | Develop API for wireless communcations | David | 2018-02-09 | 2018-02-16 | bar: WEEK 4 M to WEEK 4 F
2.2.2 | Low Power mode PSoC and Pi | Scott | 2018-02-09 | 2018-02-23 | 25% | bar: WEEK 6 M to WEEK 7 F
2.3 | ceullar data, spec sheets, & implemenation | David & Scott | 2018-02-16 | 2018-02-23 | bar: WEEK 7 M to WEEK 7 F
2.4 | Bluetooth Beacon & Display application | David & Scott | 2018-02-23 | 2018-03-02 | 0%
2.5 | Debugging & testing | David & Scott | 2018-02-23 | 2018-03-02 | bar: WEEK 8 M to WEEK 10 F
2.6 | Debugging & testing | David & Scott | 2018-03-02 | 2018-03-09
3 | Computer Vision
3.1 | Learn OpenCV & create basic CV program | Gabriel & David | 2018-01-26 | 2018-02-09 | 100% | bar: WEEK 4 M to WEEK 5 F
3.2 | Developing functions for I/O, IDing characters | Gabriel & David | 2018-02-09 | 2018-02-16 | 20% | bar: WEEK 6 M to WEEK 6 F
3.3 | Identify primary objectives | Gabriel & David | 2018-02-16 | 2018-03-02 | 0% | bar: WEEK 7 M to WEEK 8 F
4 | Mobile and Website Application
4.1 | Create an intial Cordova application | Aditya & Nelson | 2018-01-25 | 2018-01-31 | 100%
4.3 | Create a skeletal app on Cordova | Aditya | 2018-02-09 | 2018-02-16 | 100%
4.4 | Enable Payment on Mobile App | Aditya |  |  | 0%
4.5 | Research on APIs and how to use software | Aditya & Nelson |  |  | 50% | bar: WEEK 2 R to WEEK 8 T
4.6 | Push/pull information from cloud | Aditya & Nelson | 2018-02-17 | 2018-02-26 | 0% | bar: WEEK 5 M to WEEK 6 F
4.7 | Setup admin capaabilities | Nelson |  |  | 0% | bar: WEEK 7 M to WEEK 12 F
4.8 | Reserve Spots | Nelson |  |  | 0% | bar: WEEK 8 M to WEEK 9 F
4.9 | Check License Plate |  |  |  | 0% | bar: WEEK 10 M to WEEK 11 F
5 | Google Cloudstore
5.1 | Create Google Cloudstore Account | Troy Fine |  |  | 100% | bar: WEEK 4 M to WEEK 4 T
5.2 | Create and test first program | Troy Fine |  |  | 100% | bar: WEEK 4 W to WEEK 4 F
5.3 | Create API's for Pi and Cloud Comm. | Troy Fine |  |  | 30%
5.4 | Research REST API | Troy Fine |  |  | 10% | bar: WEEK 6 M to WEEK 6 F
5.5 | Research Google App Engine | Troy Fine |  |  | 10% | bar: WEEK 6 M to WEEK 6 F